## Risks
Prudentia Book Store Risk List
Risk ID | Date Identified | Headline | Description | Type | Impact | Probability | Magnitude | Owner | Mitigation Strategy
1 | 03.05.2020 | Impact of requirements changes on customers | Customers fail to understand the impact of requirements changes | Requirements | Tolerable | Moderate | Medium | Software Manager | Create a requirements need and important report
2 | 03.05.2020 | Staff Turnover | Experienced staff will leave the project before it is finished. | Organizational | Catastrophic | Low | Medium | Software Manager | Determine stuff requrements and distribute old stuff work to other suitable stuff until finding new experianced stuff; therefore all works shuold be understandable and documented for understand by other stuff
3 | 03.05.2020 | Staff's Health Problems | Key staff are ill at critical times in the project | People | Tolerable | Moderate | Medium | Software Manager | Instead of a one man doing everything, every person should be replaceable
4 | 03.05.2020 | Database Concurrency | The database used in the system cannot process as many transactions per second as expected | Technology | Serious | Moderate | High | Software Developer | Investigate the possibility of buying a higher-performance database
5 | 03.05.2020 | Bug Fix | The rate of defect repair is underestimated | Estimation | Tolerable | Moderate | Medium | Software Tester and Developer | Replace potentially defective components with bought-in components of known reliability.
6 | 03.05.2020 | Supply Chain Failure | Supply-demand balance cannot be established | Estimation | Serious | Moderate | High | Software Manager | Disributed, multiple vendors and alternative supply chains.
7 | 03.05.2020 | Tool Crash | Tool components lack stability | Tools | Tolerable | Moderate | Medium | Configuration And Change Manager | Check Tool condition periodically, determine alternative tools, if we lost interest on tool then get rid of it and use new alternative
8 | 03.05.2020 | Information Security Risk | Personal information security vulnerabilities | Security | Catastrophic | Low | Medium | Software Tester | Against to ransom attack always hold a backup. Personal info is encrypted
9 | 03.05.2020 | Conflict between executive stakeholders disrupts project | Members of executive management are combative to the project or there is a disagreement over project issues at the executive level. | Organizational | Catastrophic | Low | Medium | Software Manager | Try to fix issues with meetings
10 | 03.05.2020 | Tool Integrity | Software tools cannot be integrated | Tools | Tolerable | High | Medium | Configuration And Change Manager | If it possibble use integration tool for tool. If not then change tool with alternative one and try to integrate components from old tool
11 | 03.05.2020 | Disruptive Technologies | Displaces an established technology and shakes up the industry | Technology | Serious | Low | Medium | Configuration And Change Manager | Find how to integrate current system with the new technology
12 | 03.05.2020 | System outages | Critical systems go down. | Technology | Catastrophic | Low | High | Software Tester | Test system's units seperately, prepare backups.
13 | 03.05.2020 | Errors in key project management processes | Errors in project management such as schedule errors | Organizational | Tolerable | Moderate | Medium | Software Manager | Get expert advice people who have worked on similar projects
14 | 03.05.2020 | User interface is low quality | The user interface is buggy, slow or difficult to use. | Technology | Tolerable | High | Medium | Software Tester | Change interface with receiving feedback from peers and users
15 | 03.05.2020 | Cost forecasts are inaccurate | Inaccurate cost estimates and forecasts. | Estimation | Tolerable | Moderate | Medium | Software Manager | Use trustable estimation tools to make estimations.
16 | 03.05.2020 | Requirements Change | There will be a larger numbers of changes to the requirements than anticipated | Requirements | Tolerable | Moderate | Medium | Configuration And Change Manager | Good cofiguratin and change management avoids overheads. With outsourcing mass on stuff will be distributed
17 | 03.05.2020 | Product competition | A competitive product is marketed before the system is completed | Business | Catastrophic | Moderate | Extreme | Software Analyst | Examine compatitive product, and add more feature to your product
18 | 03.05.2020 | Estimated time to develop | The time required to develop the software is underestimated | Estimation | Serious | High | High | Software Manager | Making time estimating more realistic and consulting other stakeholders